## project
Reach Trivia Planner
[6 empty] | Day Highlight: |  |  |  |  | 26 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
[6 empty] | Dec. | [10 empty] | Jan.
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | Dec. 13: Day
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Brainstorming - Janujan | 1 | 1 | 1 | 1 | 100%
The Problem Defintion - Pavneet | 2 | 1 | 2 | 1 | 100%
Feature Description - Kevin | 2 | 1 | 5 | 1 | 100%
Resources - Janujan | 2 | 4 | 2 | 4 | 100%
UML Diagram - Janujan | 3 | 3 | 3 | 7 | 100%
Player Class Design - Kevin | 4 | 2 | 4 | 2 | 100%
Player List Class Design - Kevin | 5 | 2 | 5 | 2 | 100%
QuestionTF Class Design - Lily | 5 | 2 | 5 | 2 | 100%
QuestionMC Design - Lily | 5 | 2 | 5 | 2 | 100%
QuestionCB Design - Lily | 5 | 2 | 5 | 2 | 100%
Category Class Design - Pavneet | 6 | 2 | 6 | 2 | 100%
Quiz Class Design- Janujan | 6 | 2 | 6 | 2 | 100%
Statistics Class Design - Pavneet | 6 | 2 | 6 | 2 | 100%
Customization Class Design - Kevin | 6 | 2 | 6 | 2 | 100%
User Interface Design - Kevin | 8 | 2 | 8 | 2 | 100%
Design Touch Ups - Janujan | 10 | 2 | 10 | 2 | 100%
Design Complete Milestone
Player Class Coding - Pavneet | 12 | 3 | 12 | 1 | 100%
Questions - Lily | 12 | 3 | 12 | 1 | 100%
Category Class Coding - Pavneet | 12 | 3 | 18 | 4 | 100%
Quiz Class Coding - Janujan | 12 | 3 | 13 | 10 | 100%
QuestionCB Coding - Lily | 15 | 3 | 15 | 3 | 100%
Statistics Class Coding - Pavneet | 15 | 3 | 13 | 2 | 100%
QuestionMC Coding - Lily | 18 | 3 | 13 | 3 | 100%
Player List Class Coding - Kevin | 18 | 3 | 12 | 1 | 100%
User Interface Coding - Janujan | 18 | 6 | 13 | 11 | 100%
QuestionTF Class Coding - Lily | 21 | 3 | 16 | 3 | 100%
Code Complete Milestone
Integrated Testing - Pavneet | 24 | 2 | 24 | 2 | 100%
Software Packaging/Delivery - Kevin | 26 | 1 | 26 | 1 | 100%
Project Complete Milestone